## Slide 1
Enterprise Software Life-cycle Support System
Enterprise TFS - Software Factory NTI
Mike O’Brien, Toby Hable
August 2014

## Slide 2: NTI-Core: Software Life-cycle Support System
Technology:
Establish a Software Life-cycle Support System (SLSS) by leveraging Microsoft Team Foundation Server (TFS).
Objectives:
Engage Microsoft Consulting
Deploy and Verify Service
Engage and Train IT Ops Team
Initiate migration of HISD Team Projects
Migration of SEMSTFS Teams
Businesses – HISD, TSSD, IPD
Status: Service Implementation (Sept – Dec)
Resources: $200 K
3.0 FTE for
  Mike O’Brien 1.0 FTE
  Don Carlson 0.5 FTE
  New Hire for DevOps Team 1.0 FTE
  DevOps Offshore resource 0.5 FTE
  Dave Schaller – HISD
  Scott Howard – HISD
Microsoft Consulting $180 k
Total funding request $380 K
Key SEMS Contact: Mike O’Brien

## Slide 3: ETFS Timeline
Apr
May
Jun
2014
May
Jun
July
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Today
HIS Target for all TFS teams migrated
March
Service Available
Startup Investment
Sept
Pre-NTI
May 5
Jan
Define
Implementation
Ongoing
All HIS teams migrated
March

## Slide 4: ETFS Timeline
Define Service (Done!)
  System Requirements
  Definition of the Service
  Draft of ‘Cost of Service’
  Engaged additional candidate Divisions
  System Architecture
  Draft of Service Level Agreement (SLA)
  CTOC Presentation
Investments Made
  Dedicated resource working since 5/5
  Weekly update meetings with HIS
  Leveraging existing IT Team for Operations
  IT can manage TFS licenses
  Leveraging existing 3M IT infrastructure

## Slide 5: ETFS Timeline – Service Implementation
Service Implementation (Sept – Dec)
  New Hire - DevOps resource
  Startup cost – engage Microsoft Consulting for implementation and verification of service: $180k
  IT Operations Team – support of service 24 x 7 x 365 – Train Team
  Begin migration of Division Teams
Objective and Deliverable | Hours -Low | Hours -High | Rate ($) | Cost -Low | Cost -High
TFS Infrastructure Planning and Validation |  |  |  |  | 
- TFS Usage Scenarios | 40 | 40 | 300 | $ 12,000 | $ 12,000
- TFS Infrastructure Plan | 24 | 24 | 300 | $ 7,200 | $ 7,200
- TFS Administration | 40 | 60 | 300 | $ 12,000 | $ 18,000
- TFS Installation Assistance including integrations ( Low estimate is for just the installation verification) | 20 | 80 | 300 | $ 6,000 | $ 24,000
- Architect/EM oversight | 24 | 40 | 340 | $ 8,160 | $ 13,600
Total | 148 | 244 |  | $ 45,360 | $ 74,800
TFS as a Service - Governance |  |  |  |  | 
- Shared Service Security Planning | 40 | 80 | 300 | $ 12,000 | $ 24,000
- Process Governance | 40 | 80 | 300 | $ 12,000 | $ 24,000
- Build Service Governance | 40 | 40 | 300 | $ 12,000 | $ 12,000
- Integration and Reporting Governance | 40 | 40 | 300 | $ 12,000 | $ 12,000
- Architect/EM oversight | 32 | 48 | 340 | $ 10,880 | $ 16,320
Total | 192 | 288 |  | $ 58,880 | $ 88,320
TFS as a Service - Team Onboarding |  |  |  |  | 
- Team on boarding process | 40 | 80 | 300 | $ 12,000 | $ 24,000
- Source Code Migration Strategy | 40 | 40 | 300 | $ 12,000 | $ 12,000
- Pilot Team on boarding assistance | 120 | 200 | 300 | $ 36,000 | $ 60,000
- Architect/EM oversight | 40 | 64 | 340 | $ 13,600 | $ 21,760
Total | 240 | 384 |  | $ 73,600 | $ 117,760
Grand total* | 580 | 916 |  | $ 177,840 | $ 280,880

## Slide 6: ETFS Timeline
Ongoing Service (Jan 2015 – Future)
  Service available – open to all divisions/business groups/teams
  $10/user per month
    IT Operations Team cost
    Assumes no additional resources needed
  Time & Material for Custom work (by DevOps Team)
    New Team Onboarding - Migration and Training
    Integrations
    Extension to existing ETFS

## Slide 7: ETFS Timeline – Ongoing Costs
# Ops Resources | Cost / Resource | # Service Manager Resources | Cost / Resource | Total Labor | Total Team Size | Monthly Infrastructure Cost | Total Cost | Number of Users | Annual Charge per User | Monthly Cost/User
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 100 | $1,415.00 | $117.92
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 200 | $707.50 | $58.96
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 300 | $471.67 | $39.31
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 400 | $353.75 | $29.48
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 500 | $283.00 | $23.58
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 600 | $235.83 | $19.65
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 700 | $202.14 | $16.85
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 800 | $176.88 | $14.74
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 900 | $157.22 | $13.10
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1000 | $141.50 | $11.79
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1100 | $128.64 | $10.72
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1200 | $117.92 | $9.83
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1300 | $108.85 | $9.07
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1400 | $101.07 | $8.42
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1500 | $94.33 | $7.86
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1600 | $88.44 | $7.37
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1700 | $83.24 | $6.94
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1800 | $78.61 | $6.55
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 1900 | $74.47 | $6.21
1 | 90,000 | 0.25 | 200,000 | 140,000 | 1.25 | $1,500 | 141,500 | 2000 | $70.75 | $5.90
Chart: Cost/User based on Total Users
| 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 1600 | 1700 | 1800 | 1900 | 2000
Team Size | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25
Montly Cost/User | 58.9583 | 39.3056 | 29.4792 | 23.5833 | 19.6528 | 16.8452 | 14.7396 | 13.1019 | 11.7917 | 10.7197 | 9.8264 | 9.0705 | 8.4226 | 7.8611 | 7.3698 | 6.9363 | 6.5509 | 6.2061 | 5.8958

## Slide 8: ETFS Team Structure
Service Manager
- Initial contact of new teams
- Provide training
- Maintain relationship with teams
Operations (Ops)
- IT Operations Team (Managed Infrastructure)
DevOps
- Team onboarding tasks
- Service enhancements
- Test updates/upgrades, update documentation
- Perform DevOps role for SEMS/Division teams
- ETFS System Maintenance
- Respond to support requests
- Focused on PROD system

## Slide 9: New Hire for DevOps
Role / Responsibilities:
  ETFS - Team onboarding tasks
    Migration of project artifacts to ETFS
    Configure build services
  ETFS - Service enhancements
    Deploy automated build, test, and deploy systems
    Non-Windows Builds, e.g, iOS / Android
    3rd party Source repo – offsite source depot
  SEMS - Perform DevOps role for SEMS/Division teams

## Slide 10: Recommendations for ES Workgroup
Fund ETFS and eliminate user chargeback
Create “Software Developer Center of Excellence”
  Coordinate training, demos, etc.. across groups/divisions
  Provide “JumpStart” for software projects – process training, templates, app lifecycle recommendations
  Communicate software teams successes and learnings – what works, what’s not
  License purchasing coordination – purchase in volume
  Rollup reporting across projects & divisions – insights into improvement

## Slide 11: Task Timeline
Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July
Cost
Install QA/PROD
IT Ops Team Training
Build Team Onboarding Queue
Onboard HIS Teams
Onboard SEMSTFS teams
Migration Tool Investigation
Service Available
Jan

## Slide 12: Setup Investment
Startup cost – bring in Microsoft Consulting for implementation and consultation of service setup and verification: $180k
Objective and Deliverable | Hours -Low | Hours -High | Rate ($) | Cost -Low | Cost -High
TFS Infrastructure Planning and Validation |  |  |  |  | 
- TFS Usage Scenarios | 40 | 40 | 300 | $ 12,000 | $ 12,000
- TFS Infrastructure Plan | 24 | 24 | 300 | $ 7,200 | $ 7,200
- TFS Administration | 40 | 60 | 300 | $ 12,000 | $ 18,000
- TFS Installation Assistance including integrations ( Low estimate is for just the installation verification) | 20 | 80 | 300 | $ 6,000 | $ 24,000
- Architect/EM oversight | 24 | 40 | 340 | $ 8,160 | $ 13,600
Total | 148 | 244 |  | $ 45,360 | $ 74,800
TFS as a Service - Governance |  |  |  |  | 
- Shared Service Security Planning | 40 | 80 | 300 | $ 12,000 | $ 24,000
- Process Governance | 40 | 80 | 300 | $ 12,000 | $ 24,000
- Build Service Governance | 40 | 40 | 300 | $ 12,000 | $ 12,000
- Integration and Reporting Governance | 40 | 40 | 300 | $ 12,000 | $ 12,000
- Architect/EM oversight | 32 | 48 | 340 | $ 10,880 | $ 16,320
Total | 192 | 288 |  | $ 58,880 | $ 88,320
TFS as a Service - Team Onboarding |  |  |  |  | 
- Team on boarding process | 40 | 80 | 300 | $ 12,000 | $ 24,000
- Source Code Migration Strategy | 40 | 40 | 300 | $ 12,000 | $ 12,000
- Pilot Team on boarding assistance | 120 | 200 | 300 | $ 36,000 | $ 60,000
- Architect/EM oversight | 40 | 64 | 340 | $ 13,600 | $ 21,760
Total | 240 | 384 |  | $ 73,600 | $ 117,760
Grand total* | 580 | 916 |  | $ 177,840 | $ 280,880

## Slide 13: Technology Platform and Roadmap
TFS Technology
Platform
Value Added
Test Case Management
Build Automation
Version Control
Requirements Management
Project Management
TFS
Reporting
Enterprise Software Development Process
Requirements
Authoring Requirements document with Enterprise defined structure, methodology, and process
DevOps
Automated build, deploy and testing harnesses
Rollup Reporting
(self-service reporting portal)
Cross Platform Builds
(iOS / Xamarian / Android / Linux)
Cloud Hybridization
Process Template

## Slide 14: Benefits of Enterprise TFS Solution
Centralized Repository
  High Availability
  Improved Disaster Recovery
  Increased collaboration/sharing
  Reduced cost
Support Specialists – customization, maintenance and support
Visibility – customized Key Performance Indicators (KPI’s)
Training – increased knowledge of capabilities
Infography created by InCycle Software
Source information from Forrester: The Total, Economic Impact of Microsoft Application Life Cycle Mangement
Notes: Dell case study – ROI: 225% Payback: 6 months
CollabNet case study: ROI 225% Payback: 12 months
Key benefits from case studies?