## MSF CMMI xRef
CMMI
Workstream | Activity | Level | PA | Goal | Prac | Comment
Tracks
Envision
Planning
Define/update Test Approach
Build
Stabilize
| Triage Bugs | 3 | VER | 3 | 3.2
|  | 3 | VAL | 2 | 2.2
|  | 2 | CM | 2 | 2.2
Deploy
Operational Management
| Operations Review | 2 | MA | 2 | 2.2
|  | 2 | MA | 2 | 2.4
|  | 2 | PMC | 1 | 1.6
|  | 3 | IPM | 1 | 1.4
|  | 4 | QPM | 1 | 1.4
|  | 4 | QPM | 2 | 2.1 | indirect
|  | 4 | QPM | 2 | 2.2 | via whitepaper
|  | 4 | QPM | 2 | 2.3 | via whitepaper
|  | 4 | OPP | 1 | 1.1
|  | 4 | OPP | 1 | 1.2
|  | 5 | OID | 1 | 1.1
|  | 5 | OID | 1 | 1.2
|  | 5 | CAR | 1 | 1.1
| Team Meeting(s) | 2 | MA | 2 | 2.2 | Manage Project woven into many activities
|  | 2 | PMC | 1 | 1.1
|  | 2 | PMC | 1 | 1.2
| Monitor Data Management | 2 | PMC | 1 | 1.4
| Collect & Store Data | 2 | MA | 2 | 2.1
| (includes Store Data and Results) | 2 | MA | 2 | 2.3
| Manage Stakeholder Involvement | 3 | IPM | 2 | 2.1
|  | 2 | PMC | 1 | 1.5
| IPMO Meeting |  |  |  |  | multi-project co-ordination, equivalent of Scrum of Scrums
| (includes Manage Dependencies) | 3 | IPM | 2 | 2.2
|  | 2 | PMC | 1 | 1.6
|  | 3 | IT | 2 | 2.5
|  | 3 | IPM | 1 | 1.4
|  | 3 | IPM | 2 | 2.3
Governance
| Track/Milestone Review | 2 | PMC | 1 | 1.7 | for governance
| Conduct Project Retrospective | 3 | OPF | 1 | 1.3
Analysis
| Design and Development Analysis | 2 | PP | 1 | 1.1
| Test Planning | 2 | PP | 1 | 1.1
| User Experience Work Breakdown Schedule | 2 | PP | 1 | 1.1
| User Education Work Breakdown Schedule | 2 | PP | 1 | 1.1
Baseline Configuration Management
| Create Configuration Management Plan | 2 | CM | 1 | 1.1
|  | 2 | GG | 2 | 2.2
|  | 2 | GG | 2 | 2.4
| Review Configuration Management Guidelines | 2 | CM | 1 | 1.1
|  | 2 | VER | 2 | 2.2
|  | 3 | IPM | 2 | 2.2
| Establish Configuration Management System | 2 | CM | 1 | 1.2
|  | 2 | CM | 2 | 2.1
| Establish Configuration Management Access Control Policy | 2 | CM | 1 | 1.2
| Establish Configuration Management Records | 2 | CM | 1 | 1.2
|  | 2 | CM | 1 | 1.3
|  | 2 | CM | 3 | 3.1
Build a Product
| Accept a Build | 2 | CM | 1 | 1.3
|  | 3 | PI | 3 | 3.1 | moved, a.k.a. Confirm Readiness of Product Components for Integration
| Start a Build | 3 | PI | 3 | 3.2 | a.k.a. Assemble Product Components
| Verify a Build | 3 | PI | 3 | 3.3 | a.k.a. Integration Test
Fix a Build
Capture Product Vision |  | 3 | IPM | 3 | 3.2
| Write Vision Statement | 3 | IPM | 3 | 3.2
|  | 3 | IT | 2 | 2.1
| Define Personas | 3 | IPM | 3 | 3.2
|  | 3 | IT | 2 | 2.1
| Develop Lifestyle Snapshot | 3 | RD | 1 | 1.1 | Elicit Needs, Establish Operational Scenarios
|  | 3 | RD | 3 | 3.1
| Review Vision Statement | 3 | IPM | 2 | 2.1
|  | 3 | VER | 2 | 2.2
Close a Bug
| Verify a Fix | 3 | VER | 3 | 3.1 | Perform Test
Close a Bug
Create a Quality of Service Requirement
| Brainstorm Quality of Service Requirements | 2 | REQM | 1 | 1.1 | Understanding Requirements. Elicit Needs
|  | 3 | RD | 1 | 1.1
|  | 3 | RD | 1 | 1.2
| Prioritize Quality of Service Requirement | 3 | RD | 3 | 3.4
| Write Quality of Service Requirement | 3 | RD | 3 | 3.1
| Validate Quality of Service Requirement | 3 | RD | 3 | 3.5 | Develop Requirements
| Write User Acceptance Test | 3 | VAL | 1 | 1.3 | Develop Requirements
Create a Scenario
| Brainstorm Scenarios | 2 | REQM | 1 | 1.1 | Understanding Requirements, Elicit Needs, Establish Operational Scenarios
|  | 3 | RD | 1 | 1.1
|  | 3 | RD | 1 | 1.2
|  | 3 | TS | 1 | 1.2
| Prioritize Scenarios | 3 | RD | 3 | 3.4
| Write Scenarios | 3 | RD | 3 | 3.1
|  | 3 | TS | 1 | 1.2
| Storyboard Scenarios | 3 | RD | 3 | 3.1
|  | 3 | TS | 1 | 1.2
| Validate Scenarios | 3 | RD | 3 | 3.5
| Write User Acceptance Tests | 3 | VAL | 1 | 1.3
Create Product Requirements
| Allocate Product Component Requirements | 3 | RD | 2 | 2.2
| Define Interface Requirements | 3 | RD | 2 | 2.3
|  | 3 | RD | 3 | 3.2
| Define Security Requirements | 3 | RD | 2 | 2.1
|  | 3 | RD | 3 | 3.2
| Define Safety Requirements | 3 | RD | 2 | 2.1
| Develop a Domain Model | 3 | RD | 3 | 3.2
|  | 3 | RD | 3 | 3.3
|  | 3 | RD | 3 | 3.4
|  | 3 | TS | 1 | 1.2
| Develop a User Interface flow Model | 3 | RD | 3 | 3.3
|  | 3 | RD | 3 | 3.4
| Define Functional Requirements | 3 | RD | 2 | 2.1 | using the domain model and UI models as input
|  | 3 | RD | 3 | 3.2
| Define Operational Requirements | 3 | RD | 3 | 3.1
|  | 3 | TS | 1 | 1.2
|  | 3 | RD | 3 | 3.2
| Prioritize Functionality | 3 | RD | 3 | 3.4
| Validate Requirements | 3 | RD | 3 | 3.5
Create Solution Architecture
| Create Alternative Application Partitioning Designs | 3 | TS | 2 | 2.1 | Design Product (architecture)
|  | 3 | TS | 1 | 1.1
|  | 3 | DAR | 1 | 1.3
| Design System Architecture & Deployment | 3 | TS | 2 | 2.3
| Develop Threat Model | 3 | TS | 2 | 2.1
| Develop Performance Model | 3 | TS | 2 | 2.1
| Create Proof of Concepts | 3 | TS | 1 | 1.1 | Develop Detailed Alternative Solutions
| Assess Alternatives (LAAAM) | 3 | DAR | 1 | 1.1 | LAAAM
|  | 3 | DAR | 1 | 1.2 | LAAAM
|  | 3 | DAR | 1 | 1.4 | LAAAM
|  | 3 | DAR | 1 | 1.5 | LAAAM
| Select Architecture | 3 | TS | 1 | 1.3 | includes Perform Make vs. Buy or Reuse Analysis
|  | 3 | DAR | 1 | 1.6
| Make, Buy or Reuse Analysis | 3 | TS | 2 | 2.4
| Prepare for Review of System Architecture | 3 | VER | 2 | 2.1
| Review System Architecture & Deployment | 3 | PI | 2 | 2.1
|  | 3 | VER | 2 | 2.2
| Create Infrastructure Architecture & Documentation/Guidelines | 3 | TS | 2 | 2.2 | included in Establish a Technical Data Package
| Architecture Control Board Meeting | 3 | PI | 2 | 2.2
Develop Documentation
| Create Documentation Outlines | 3 | TS | 3 | 3.2
| Create Documentation Plan | 2 | GG | 2 | 2.2
| Write Documentation | 3 | TS | 3 | 3.2
| Edit Documentation | 3 | TS | 3 | 3.2
| Peer Review Documentation | 3 | TS | 3 | 3.2
| Test Documentation | 3 | TS | 3 | 3.2
Establish Environments
| Plan Product Integration | 3 | PI | 1 | 1.1
| Establish Integration Environment | 3 | PI | 1 | 1.2
|  | 3 | PI | 1 | 1.3
| Establish a Unit Test Environment | 3 | VER | 1 | 1.2
| Verify Integration Environment | 3 | PI | 1 | 1.2
| Select Static Analysis Rules and Guidelines | 3 | VER | 2 | 2.3 | indirect
|  | 5 | CAR | 2 | 2.1
| Select Project Coding Guidelines | 3 | VER | 2 | 2.3 | indirect
|  | 5 | CAR | 2 | 2.1
| Establish Project Verification Guidelines | 3 | VER | 1 | 1.3
Establish Project Process | [5 empty] | Includes Project Data Management
| Select Project Process Template | 3 | OPD | 1 | 1.1 | indirect evidence
|  | 3 | OPD | 1 | 1.2 | indirect evidence
|  | 3 | IPM | 1 | 1.2
|  | 2 | PP | 1 | 1.3
|  | 3 | IPM | 1 | 1.1
| Tailor Project Process | 3 | OPD | 1 | 1.3
|  | 3 | IT | 2 | 2.4
| Review Project Process | 3 | VER | 2 | 2.3
|  | 3 | OPD | 1 | 1.1
| Establish Measurement Plan | 2 | MA | 1 | 1.1
| Establish Project Data Management Plan | 2 | PP | 2 | 2.3
| Monitor Measurement and Process Assets | 3 | OPD | 1 | 1.4
|  | 3 | IPM | 1 | 1.5
|  | 2 | MA | 2 | 2.1
|  | 3 | OPD | 1 | 1.5
Fix a Bug
| Reproduce the Bug | 3 | VER | 3 | 3.1
| Locate Cause of Bug | 3 | VER | 3 | 3.2
|  | 5 | CAR | 1 | 1.2
Reassign Bug
| Decide on Strategy for Fix | 3 | VER | 3 | 3.2
| Code Fix | 3 | TS | 3 | 3.1
| Write or Update a Unit Test for Bug Fix | 3 | VER | 1 | 1.3
| Perform a Unit Test for Bug Fix | 3 | VER | 3 | 3.1
| Refactor Code for Bug Fix | 3 | TS | 3 | 3.1
| Prepare for Bug Code Review | 3 | VER | 2 | 2.1
| Bug Code Review | 3 | VER | 2 | 2.2
|  | 3 | PI | 3 | 3.1
| Integrate Bug Changes | 3 | PI | 3 | 3.1
Implement a Development Task
| Cost a Development Task | 2 | PP | 1 | 1.4
| Design | 3 | TS | 2 | 2.2
| Create or Update System or Verification Test | 3 | VER | 1 | 1.3
| Prepare for Design Review | 3 | VER | 2 | 2.1
| Design Review | 3 | VER | 2 | 2.2
| Write Code | 3 | TS | 3 | 3.1
| Perform Code Analysis | 3 | VER | 2 | 2.1 | part of Prepare for Code Review
| Write or Update a Unit Test | 3 | VER | 1 | 1.3
| Perform a Unit Test | 3 | VER | 3 | 3.1
| Refactor Code | 3 | TS | 3 | 3.1
| Prepare for Code Review | 3 | VER | 2 | 2.1
| Code Review | 3 | VER | 2 | 2.2
|  | 3 | PI | 3 | 3.1
| Integrate Code Changes | 3 | PI | 3 | 3.1
Manage Change Requests | [5 empty] | a.k.a Track and Control Changes
| Create Change Request | 2 | CM | 2 | 2.1
| Analyze Change Request | 1 | REQM | 1 | 1.3
|  | 2 | CM | 2 | 2.1
| Prioritize Change Requests | 2 | CM | 2 | 2.1
| Review Change Requests | 2 | CM | 2 | 2.1 | includes CCB
|  | 3 | IPM | 2 | 2.1
|  | 3 | VER | 2 | 2.2
| Track Change Requests | 2 | CM | 2 | 2.1
|  | 2 | REQM | 1 | 1.3
Manage Issues
| Issue Log Review |  |  |  |  | a.k.a. Triage
| Analyze Issues | 2 | PMC | 2 | 2.1
| Take Corrective Action | 2 | PMC | 2 | 2.2
| Monitor Corrective Action | 2 | PMC | 2 | 2.3
| Review Action and Verify Resolution | 3 | VER | 2 | 2.2
Manage Risk
| Identify Risk | 2 | PP | 2 | 2.2
|  | 2 | RSKM | 2 | 2.1
| Analyze Risks | 2 | PP | 2 | 2.2
|  | 2 | RSKM | 2 | 2.2
| Prioritize Risks for Mitigation | 2 | PP | 2 | 2.2
|  | 2 | RSKM | 2 | 2.2
| Select Risks for Mitigation | 3 | RSKM | 3 | 3.1
| Plan Risk Mitigation | 3 | RSKM | 3 | 3.1
| Implement Mitigation Action | 3 | RSKM | 3 | 3.2
| Monitor Risks | 2 | PMC | 1 | 1.3
| Implement Contingency Plan | 2 | PMC | 2 | 2.3
Perform Quality Assurance
| Audit | 2 | PPQA | 1 | 1.1
|  | 2 | PPQA | 1 | 1.2
|  | 2 | PPQA | 2 | 2.1
|  | 2 | PPQA | 2 | 2.2
|  | 2 | CM | 3 | 3.2 | configuration audit
| Identify Inconsistencies | 2 | REQM | 1 | 1.5 | (between project work and requirements)
|  | 2 | PPQA | 1 | 1.2
| Analyze Review Minutes | 2 | PPQA | 1 | 1.2
| Review Design and Code Guidelines | 2 | PPQA | 1 | 1.1
| Track Corrective Actions to Closure | 2 | PPQA | 2 | 2.1
|  | 2 | PPQA | 2 | 2.2
Plan an Iteration
| Select Backlog | 3 | RD | 3 | 3.4
|  | 3 | VER | 1 | 1.1
Iteration Analysis
| Estimate Iteration | 2 | PP | 1 | 1.1 | (re-)Estimate Project and Establish Budget and Schedule
|  | 2 | PP | 1 | 1.2
|  | 2 | PP | 1 | 1.4
| Define Iteration Budget and Schedule | 2 | PP | 2 | 2.1
| Form Iteration Team(s) (see Feature Crew & Architectural Layers) | 3 | IT | 1 | 1.3
|  | 3 | IPM | 4 | 4.1
|  | 3 | IPM | 4 | 4.3
| Define Iteration Roles & Responsibilities | 3 | IT | 2 | 2.3
|  | 3 | IPM | 4 | 4.1
| Define Communication Plan | 3 | IPM | 4 | 4.3
|  | 3 | IT | 2 | 2.5 | indirect
| Identify Iteration Stakeholders | 3 | IPM | 2 | 2.1
| Plan Iteration Stakeholder Involvement | 2 | PP | 2 | 2.6 | Project Planning spread over 4 activities
| Plan Knowledge and Skills | 2 | PP | 2 | 2.5
|  | 3 | IT | 1 | 1.2
|  | 3 | VER | 2 | 2.3
| Plan Iteration Resources | 2 | PP | 2 | 2.4
| Iteration Plan Review | 2 | PP | 3 | 3.1
|  | 2 | PP | 2 | 2.7
| IPMO Iteration Review | 2 | PP | 3 | 3.1
|  | 2 | PP | 3 | 3.2
|  | 2 | PP | 3 | 3.3
| Obtain Iteration Commitments | 2 | REQM | 1 | 1.2
|  | 2 | PP | 3 | 3.3
| Hold Iteration Launch | 3 | IT | 2 | 2.1
|  | 3 | IT | 2 | 2.5
| Conduct Previous Iteration Retrospective | 2 | PMC | 1 | 1.6
|  | 3 | OPF | 1 | 1.3
Plan Project
| Estimate Project | 2 | PP | 1 | 1.1
|  | 2 | PP | 1 | 1.2
| Define Budget and Schedule | 2 | PP | 2 | 2.1 | Project Planning spread over 4 activities
|  | 3 | IPM | 1 | 1.2
| Determine Risk Sources and Categories | 3 | RSKM | 1 | 1.1
| Define Risk Parameters | 3 | RSKM | 1 | 1.2
| Determine Risk Management Strategy | 3 | RSKM | 1 | 1.3
| Plan Project Resources | 2 | PP | 2 | 2.4 | Project Planning spread over 4 activities
|  | 3 | IPM | 1 | 1.2
| Plan Project Knowledge and Skills | 2 | PP | 2 | 2.5
|  | 3 | IPM | 1 | 1.2
|  | 3 | IT | 1 | 1.2
| Form Project Team | 3 | IT | 1 | 1.3
|  | 3 | IPM | 4 | 4.1
|  | 3 | IPM | 4 | 4.3
|  | 3 | IT | 2 | 2.5
| Establish Project Team Charter | 3 | IT | 2 | 2.2
| Define Project Life Cycle | 2 | PP | 1 | 1.3
|  | 3 | IPM | 1 | 1.1
| Define Project Roles & Responsibilities | 3 | IT | 2 | 2.3
|  | 3 | IPM | 4 | 4.1
| Define Project Communication Plan | 3 | IT | 2 | 2.5 | indirect
|  | 3 | IPM | 4 | 4.3
| Identify Project Stakeholders | 3 | IPM | 2 | 2.1
| Plan Project Stakeholder Involvement | 2 | PP | 2 | 2.6
|  | 3 | IPM | 1 | 1.2
| Review Project Plan | 2 | VER | 2 | 2.2
|  | 2 | PP | 2 | 2.7
|  | 2 | PP | 3 | 3.1
| IPMO Plan Review | 2 | PP | 3 | 3.1 | Review other plans which affect project & Integrate Project Plan
|  | 2 | PP | 3 | 3.2 | includes reconcile work and resource levels
|  | 3 | IPM | 1 | 1.3
| Obtain Commitments | 2 | REQM | 1 | 1.2
|  | 2 | PP | 3 | 3.3
| Hold Project Launch | 3 | IT | 2 | 2.1
|  | 3 | IT | 2 | 2.5
Release a Product
| Select Release Candidate | 3 | VAL | 1 | 1.1
| (includes Analyze System Test Results) | 3 | VER | 2 | 2.2
| Establish a User Acceptance Test Environment | 3 | VAL | 1 | 1.2
| Establish Validation Guidelines | 2 | GG | 2 | 2.1
| User Acceptance Testing | 3 | VAL | 2 | 2.1 | Perform Test
| Analyze User Acceptance Test Results | 3 | VAL | 2 | 2.2
| Accept Product for Release | 3 | PI | 3 | 3.3
| Create Release Notes | 3 | PI | 3 | 3.4
| Package Product | 3 | PI | 3 | 3.4
| Create Rollout / Deployment Plan | 2 | PP | 2 | 2.4
|  | 2 | PP | 2 | 2.5
|  | 2 | PP | 2 | 2.6
|  | 2 | PP | 2 | 2.7
| Execute Rollout Plan (includes Deploy the Product) | 3 | PI | 3 | 3.4 | CMMI xRef PI 3.4 sub-practice 6 "Install the Product"
Test a Customer Requirement
| Develop Customer Requirement Tests | 3 | VAL | 1 | 1.3
|  | 3 | VER | 1 | 1.3
| Select and Run Customer Requirement Tests | 3 | VAL | 2 | 2.1
|  | 3 | VAL | 2 | 2.2
| Open a Bug for Customer Requirement | 3 | VAL | 2 | 2.2
| Conduct Exploratory Testing | 3 | RD | 1 | 1.1
|  | 2 | CM | 2 | 2.1
Verify a Product Requirement
| Develop Tests | 3 | VER | 1 | 1.3
|  | 3 | VAL | 1 | 1.3
| Select and Run Tests | 3 | VER | 3 | 3.1
|  | 3 | VER | 3 | 3.2
| Open a Bug | 3 | VER | 3 | 3.2
Work Items
Task
Change Request
Risk
Requirements
Review
Bug
Issue
Roles
Solution Architect
Business Analyst
Project Manager
Tester
Developer
Release Manager
Sponsor
Auditor
User Experience Architect
User Education Specialist (Tech Writer)
Development Manager
Test Manager
IPM Officer (Director of IPMO)
Build Engineer
Subject Matter Expert
Lead Developer
Product Manager
Infrastructure Architect
Main Pages
Concepts (Overview)
Cycles & Iterations
Mindsets
Principles
About Roles
Governance (Tracks)
Team Model
Generic Goals
Institutionalize a Managed Process
| Establish an Organizational Policy | 2 | GG | 2 | 2.1
| Plan the Process | 2 | GG | 2 | 2.2
| Provide Resources | 2 | GG | 2 | 2.3
| Assign Responsibility | 2 | GG | 2 | 2.4 | Use VSTS and MSF CMMI process
| Train People | 2 | GG | 2 | 2.5
| Manage Configurations | 2 | GG | 2 | 2.6 | Use VSTS and MSF CMMI process
| Identify and Involve Relevant Stakeholders | 2 | GG | 2 | 2.7 | Use VSTS and Project Portal
| Monitor and Control the Process | 2 | GG | 2 | 2.8 | Use VSTS Reports
| Objectively Evaluate Adherence | 2 | GG | 2 | 2.9 | Use the reports and queries
| Review Status with Higher Level Management | 2 | GG | 2 | 2.1 | Operations review, publish reports to project portal
Institutionalize a Defined Process
| Establish a Defined Process | 3 | GG | 3 | 3.1
| Collect Improvement Information | 3 | GG | 3 | 3.2 | use warehouse reports and root cause analysis from Change Requests, Issues, Tasks and Bugs
Reports & Queries |  | 2 | MA | 1 | 1.3
Active Bugs
Actual Quality versus Velocity
All My Team Project Work Items
All Tasks
All Work Items
Blocked Work Items
Bug Rates
| Bugs by Priority | 3 | VAL | 2 | 2.2
| Builds | 3 | PI | 3 | 3.2
| Change Requests | 2 | REQM | 1 | 1.3
| Corrective Actions | 2 | PMC | 2 | 2.3
| Customer Requirements | 2 | REQM | 1 | 1.3
Development Tasks
| Issues | 3 | IPM | 1 | 1.4
| Mitigation Action Status | 3 | RSKM | 3 | 3.2
My Work Items
Open Issues and Blocked Work Items Trend
| Product Requirements | 2 | REQM | 1 | 1.3
| Quality Indicators | 2 | PPQA | 2 | 2.1
Reactivations
Regressions
Related Work Items
Remaining Work
| Requirements Test History | 3 | VAL | 2 | 2.2
Resolved Bugs
| Reviews | 2 | PPQA | 3 | 3.1
| Risks | 2 | PPQA | 2 | 2.2
Scenario Details
| Tasks | 2 | PPQA | 1 | 1.1
| Test Failures Without Active Bug | 3 | PI | 3 | 3.3
Test Passing With Active Bug
| Test Tasks | 3 | VAL | 1 | 1.2 | Filter by link to customer or product requirements
Triage
Unplanned Work
Velocity
|  | 3 | VER | 2 | 2.2
|  | 2 | PPQA | 2 | 2.2
|  | 2 | PPQA | 2 | 2.2
|  | 3 | VER | 3 | 3.2
|  | 3 | VAL | 1 | 1.3
|  | 3 | VAL | 2 | 2.1
|  | 3 | VAL | 2 | 2.2
|  | 2 | CM | 2 | 2.1
|  | 2 | CM | 3 | 3.1
|  | 2 | PMC | 1 | 1.3
|  | 3 | RSKM | 2 | 2.1
|  | 3 | RSKM | 2 | 2.2
|  | 3 | RSKM | 3 | 3.1
|  | 2 | PMC | 1 | 1.7
|  | 3 | RD | 3 | 3.5
|  | 3 | VER | 2 | 2.2
|  | 2 | PMC | 1 | 1.5
|  | 3 | IPM | 2 | 2.3
|  | 2 | PMC | 2 | 2.1
Work Items
Work Items by Owner
Work Items by State
How To
Reassign a Bug
Resolve a Bug
Create a Bug Report
Create a Scenario List in Excel
Create a Quality of Service Requirement List in Excel
Create a Bug List
Work Products
| Application Diagram | 3 | PI | 2 | 2.1
|  | 3 | TS | 1 | 1.2
|  | 3 | TS | 2 | 2.1
| Architecture Alternative Solutions Proposal | 3 | TS | 1 | 1.1
Audit Plan
Audit Report
| Changeset | 3 | PI | 1 | 1.3
| Commitments | 2 | PP | 3 | 3.3
|  | 2 | REQM | 1 | 1.2
| Communication Plan | 3 | IT | 2 | 2.5
| Configuration Audit Results | 2 | CM | 3 | 3.2
| Corrective Action Plan | 2 | PMC | 2 | 2.2
| Delivery Documentation | 3 | PI | 3 | 3.4
Deployment Plan
Documentation Plan
| Domain Model | 3 | RD | 3 | 3.2
|  | 3 | TS | 1 | 1.2
| Improvement Suggestion | 3 | IPM | 1 | 1.5
Iteration Plan
Knowledge and Skills Plan
| LAAAM Assessment Matrix | 3 | TS | 1 | 1.1
| Lessons Learned | 2 | PMC | 1 | 1.7
|  | 3 | IPM | 1 | 1.4
| Lifestyle Snapshot | 3 | RD | 1 | 1.1
Load Test
| Logical Datacenter Diagram | 3 | TS | 2 | 2.1
| Manual Test | 3 | VER | 1 | 1.1
| Master Schedule | 3 | IPM | 1 | 1.3
|  | 3 | IT | 2 | 2.5
Meeting Minutes
| Operations Review Presentation | 2 | MA | 2 | 2.4
Organization Coding Guidelines
| Peer Review Checklist | 3 | VER | 2 | 2.1
| Peer Review Exception Review Minutes | 3 | VER | 2 | 2.2
| Persona | 3 | RD | 1 | 1.1
Product Documentation
Product Integration Plan
| Product Integration Sequence | 3 | PI | 1 | 1.1 | Team Build script
Project Coding Guidelines
Project Organization Chart
| Project Plan | 2 | PP | 2 | 2.7
|  | 3 | IPM | 1 | 1.2
| Risk Categories and Sources | 3 | RSKM | 1 | 1.1
Risk Management Strategy
| Shared Vision Evangelization Presentation | 3 | IT | 2 | 2.1
| Stakeholder Involvement Plan | 2 | PP | 2 | 2.6
(help text reference) | Static Analysis Guidelines |  |  |  |  | ms-help://MS.VSCC.v80/MS.MSDNQTR.v80.en/MS.MSDN.v80/MS.VSENT.v80.en/dv_vsetsa01/html/bae90152-0234-402f-b72e-e9da93ca8f31.htm
(help text reference) | Static Analysis Rules |  |  |  |  | ms-help://MS.VSCC.v80/MS.MSDNQTR.v80.en/MS.MSDN.v80/MS.VSENT.v80.en/dv_vsetsa01/html/bae90152-0234-402f-b72e-e9da93ca8f31.htm
Storyboard
| System Diagram | 3 | PI | 2 | 2.1
|  | 3 | TS | 1 | 1.2
|  | 3 | TS | 2 | 2.1
| Team Charter Document | 3 | IT | 2 | 2.2
| Test Approach | 3 | VER | 1 | 1.1
| Threat Model | 3 | RD | 1 | 1.2 | Customer Requirements
| User Interface Flow Model | 3 | RD | 3 | 3.2
| Unit Test | 3 | VER | 1 | 1.1
Vision Document
Web Test

## CMMI Gap Analysis
Level | PA | SG | SP | Title | Gap | Workstream | Activity | Direct Evidence | Indirect Evidence
2 | REQM | 1 |  | Manage Requirements
2 | REQM | 1 | 1.1 | Obtain an understanding of requirements |  | Create Scenario | Brainstorm Scenarios | Requirements WIs | Validate Requirements review minutes
[6 empty] | Create QoS Requirement | Brainstorm Quality of Service Requirements
2 | REQM | 1 | 1.2 | Obtain Commitment to Requirements |  | Plan Iteration | Obtain Commitments | ??? | IPMO Review minutes, Iteration/Project Plan Review minutes
[6 empty] | Plan Project | Obtain Commitments
2 | REQM | 1 | 1.3 | Manage Requirements Changes |  | Manage Change Requests | Analyze Change Request | Change Request WI's revision history | Requirements query/report
2 | REQM | 1 | 1.4 | Maintain Bidirectional Traceability of Requirements | x
2 | REQM | 1 | 1.5 | Identify Inconsistencies between Project Work and Requirements |  | Operational Management Track | Identify Inconsistencies | Inconsistencies Report | Identify inconsistency activities as task histories
2 | PP | 1 |  | Establish Estimates
2 | PP | 1 | 1.1 | Estimate Scope of Project |  | Analysis | Design and Development Analysis | Task WI's
[6 empty] | Analysis | Test Planning
[6 empty] | Analysis | Ux Work Breakdown
[6 empty] | Analysis | UE Work Breakdown
[6 empty] | Plan Iteration | Estimate Iteration |  | Estimate (work product)
[6 empty] | Plan Project | Estimate Project |  | Estimate (work product)
2 | PP | 1 | 1.2 | Establish Estimates of Work Product and Task Attributes |  | Plan Iteration | Estimate Iteration | Estimate (work product) | Iteration Plan Review Minutes (WI query/report)
[6 empty] | Plan Project | Estimate Project | Estimate (work product) | Project Plan Review Minutes (WI query/report)
2 | PP | 1 | 1.3 | Define the Project Lifecycle |  | Plan Project | Define Project Lifecycle
[6 empty] | Establish Project Process |  | Process Template (project specific) | Process Template (MSF standard), Process designs (Visio EDOC flows)
2 | PP | 1 | 1.4 | Determine Estimates of Effort and Cost |  | Implement a Developer Task | Cost a Dev Task | Task WI level of effort estimates (Task query), Velocity report, statistical analysis on velocity report (optional work product) | Estimation Rationale (in guidance or work product)
2 | PP | 2 |  | Develop a Project Plan
2 | PP | 2 | 2.1 | Establish the Budget and Schedule |  | Plan Iteration | Define Budget and Schedule | Project Plan (work product) | Project Plan Review Minutes (work product), IPMO Meeting Minutes
[6 empty] | Plan Project | Estimate Budget and Schedule | Iteration Plan (work product) | Iteration Plan Review Minutes (work product), IPMO Meeting Minutes
2 | PP | 2 | 2.2 | Identify Project Risks |  | Risk Management | Identify Risks | Risk WI query | Risk categories and sources, criteria for analysis
[6 empty] | Risk Management | Analyze Risks | Risk Analysis - field on Risk WI
[6 empty] | Risk Management | Prioritize Risks | Risk WI history
2 | PP | 2 | 2.3 | Plan for Data Management |  | Establish Project Process | Establish Project Data Management Plan | Data Management Plan (work product), process guidance reports, project portal actual reports, work item type definitions | work item database, data warehouse, work item type definitions
2 | PP | 2 | 2.4 | Plan for Project Resources |  | Plan Iteration | Plan Resources | staffing, facilities and equipment plan (work product) | Iteration Plan Review Minutes (work product), IPMO Meeting Minutes
[6 empty] | Plan Project | Plan Resources | staffing, facilities and equipment plan (work product) | Project Plan Review Minutes (work product), IPMO Meeting Minutes
[6 empty] | Release a Product | Create Rollout and Deployment Plan | rollout or deployment plan (work product)
2 | PP | 2 | 2.5 | Plan for Needed Knowledge and Skills |  | Plan Iteration | Plan Knowledge/Skills | Knowledge and skills plan (work product) | Not covered
[6 empty] | Plan Project | Plan Knowledge/Skills | Knowledge and skills plan (work product) | Not covered
[6 empty] | Release a Product | Create Rollout and Deployment Plan | Knowledge and skills plan (work product) | Not covered
2 | PP | 2 | 2.6 | Plan Stakeholder Involvement |  | Plan Iteration | Plan Stakeholder Involvement | Stakeholder Involvement Plan (work product) | Review WI (type==meeting) attendee lists, Issue WI's where stakeholder involvement is questioned
[6 empty] | Plan Project | Plan Stakeholder Involvement | Stakeholder Involvement Plan (work product) | Review WI (type==meeting) attendee lists, Issue WI's where stakeholder involvement is questioned
[6 empty] | Release a Product | Create Rollout and Deployment Plan | Stakeholder Involvement Plan (work product)
2 | PP | 2 | 2.7 | Establish the Project Plan |  | Plan Project | Project Plan Review | Project Plan (work product) | Review minutes (work product)
[6 empty] | Plan Iteration | Iteration Plan Review | Project Plan (work product) | Review minutes (work product)
[6 empty] | Release a Product | Create Rollout and Deployment Plan | Project Plan (work product) | Review minutes (work product)
2 | PP | 3 |  | Obtain Commitment to Plan
2 | PP | 3 | 3.1 | Review Plans that Affect the Project |  | Plan Iteration | Iteration Plan Review | Review WI | Review minutes (work product)
[6 empty] | Plan Iteration | IPMO Review | IPMO Meeting Task WI | IPMO Meeting minutes
[6 empty] | Plan Project | IPMO Review | IPMO Meeting Task WI | IPMO Meeting minutes
2 | PP | 3 | 3.2 | Reconcile Work and Resource Levels |  | Plan Project | IPMO Review | Revised Budget, Schedule, Requirements, Stakeholder commitments | Project plan revision history, Change Requests, Master Schedule
2 | PP | 3 | 3.3 | Obtain Plan Commitment |  | Plan Iteration | IPMO Review | ??? | IPMO Meeting minutes
[6 empty] | Plan Iteration | Obtain Commitments | ??? | IPMO Meeting minutes
[6 empty] | Plan Project | Obtain Commitments | ??? | IPMO Meeting minutes
2 | PMC | 1 |  | Monitor Project Against Plan
2 | PMC | 1 | 1.1 | Monitor Project Planning Parameters |  | Operational Management Track | Daily Team Meeting | Reports | Historical Reports
2 | PMC | 1 | 1.2 | Monitor Commitments |  | Operational Management Track | Daily Team Meeting | Reports | Team Foundation WI's tracking, Project Plan, Iteration Plan
2 | PMC | 1 | 1.3 | Monitor Project Risks |  | Risk Management | Monitor Risks | Risk WI's | Risk Status Report
2 | PMC | 1 | 1.4 | Monitor Data Management |  | Operational Management Track | Monitor Data Management | Reports, WI queries | Operations Review minutes
2 | PMC | 1 | 1.5 | Monitor Stakeholder Involvement |  | Operational Management Track | Manage Stakeholder Involvement | Issue WI's, Review WI's (type==meeting) | Monitor Stakeholder Involvement Task WI's
2 | PMC | 1 | 1.6 | Conduct Progress Reviews |  | Operational Management Track | Operations Review | Operations Review meeting minutes, IPMO meeting minutes, Reports | Project Retrospective minutes, Iteration Retrospective minutes
[6 empty] | Operational Management Track | IPMO Meeting
2 | PMC | 1 | 1.7 | Conduct Milestone Reviews |  | Governance Track | Track/Milestone Review | Milestone Review Task WI's, Iteration Retrospective WI's | Milestone Review meeting minutes, Iteration Review Meeting Minutes
2 | PMC | 2 |  | Manage Corrective Action to Closure
2 | PMC | 2 | 2.1 | Analyze Issues |  | Issue Management | Analyze Issues | Issue WI's (query showing "active") | Issue history showing analysis completed
2 | PMC | 2 | 2.2 | Take Corrective Action |  | Issue Management | Take Corrective Action | Task WI's (type==Corrective Action) | Issue history showing status, Task history showing progress on corrective action
2 | PMC | 2 | 2.3 | Manage Corrective Action |  | Issue Management | Monitor Corrective Action | Issues and Blocking WI's Report | Corrective Action Review Task WI's and Issue WI's history
[6 empty] | Risk Management | Implement Contingency Plan | Contingency Plan Task WI's | Contingency Plan WI history
2 | MA | 1 |  | Align Measurement and Analysis Activities
2 | MA | 1 | 1.1 | Establish Measurement Objectives |  | Establish Project Process | Establish Measurement Plan | Project Guidance (general MSF overview material and specific report guidance) | Project Guidance (alignment)
2 | MA | 1 | 1.2 | Specify Measures |  | Reports |  | Reports Guidance | Reports Guidance
2 | MA | 1 | 1.3 | Specify Data Collection and Storage Procedures |  | Reports |  | Process Template and WITDs | Team Foundation Server
2 | MA | 1 | 1.4 | Specify Analysis Procedures |  | Reports |  | Reports Guidance | Rosetta, data warehouse
2 | MA | 2 |  | Provide Measurement Results
2 | MA | 2 | 2.1 | Collect Measurement Data |  | Establish Project Process | Populate Organization Measurement Repository | Work Items, Reports | Team Foundation Operational Data Store, Data warehouse
[6 empty] | Operational Management Track | Collect and Store Data
2 | MA | 2 | 2.2 | Analyze Measurement Data |  | Operational Management Track | Operations Review | Reports | Operations Review minutes
2 | MA | 2 | 2.3 | Store Data and Results |  | Operational Management Track | Collect and Store Data | WI inventory query/report, data warehouse, operations review presentation (work product) | Operations Review minutes
2 | MA | 2 | 2.4 | Communicate Results |  | Operational Management Track | Operations Review | Operations Review presentations (work product) | Operations Review minutes
2 | PPQA | 1 |  | Objectively Evaluate Processes and Work Products
2 | PPQA | 1 | 1.1 | Objectively Evaluate Processes and Work Products |  | Governance Track | Audit | Audit Report (work product) | Corrective Actions, Improvement Suggestions
[6 empty] | Establish Project Process | Evaluate Process |  | Project process template revision history
2 | PPQA | 1 | 1.2 | Objectively Evaluate Work Products and Services |  | Governance Track | Audit | Audit Report (work product) | Corrective Actions, Improvement Suggestions
[6 empty] | Establish Project Process | Evaluate Process |  | Project process template revision history
2 | PPQA | 2 |  | Provide Objective Insight
2 | PPQA | 2 | 2.1 | Communicate and Ensure Resolution of Noncompliance Issues | x
2 | PPQA | 2 | 2.2 | Establish Records |  | Governance Track | Audit | Audit Report (work product) | Reports, Corrective Actions, Improvement Suggestions
2 | CM | 1 |  | Establish Baselines
2 | CM | 1 | 1.1 | Identify Configuration Items |  | Baseline Configuration Management | Create Configuration Management Plan | Process Guidance - work items and work products | CCB Meeting minutes - query/report of Review Wis
2 | CM | 1 | 1.2 | Establish a Configuration Management System |  | Baseline Configuration Management | Establish Configuration Management System | Process Template, Work groups and access policies, Change Request Wis, CM Process Guidance workstream | Data warehouse, TFS Backup
[6 empty] | Baseline Configuration Management | Establish Configuration Management Policy | Configuration Management Baseline Report
2 | CM | 1 | 1.3 | Create or Release Baselines | x
2 | CM | 2 |  | Track and Control Changes
2 | CM | 2 | 2.1 | Track Change Requests |  | Manage Change Requests | Create Change Request | Change Request WI's Query/Report
[6 empty] | Manage Change Requests | Prioritize Change Requests | CCB Meeting Minutes (Review WI)
[6 empty] | Manage Change Requests | Analyze Change Requests |  | Change Request Impact Analysis - field on WI
[6 empty] | Test a Customer Requirements (Scenario or QoS) | Conduct Exploratory Testing |  | Test Results (Task WIs)
2 | CM | 2 | 2.2 | Control Configuration Items | x
2 | CM | 3 |  | Establish Integrity
2 | CM | 3 | 3.1 | Establish Configuration Records |  | Baseline Configuration Management | Establish Configuration Management Records | Team System Version Control
2 | CM | 3 | 3.2 | Perform Configuration Audits |  | Governance Track | Audit | Configuration Audit Results (work product) | Improvement Suggestions (work product or work item)
2 | SAM | 1 |  | Establish Supplier Agreements
2 | SAM | 1 | 1.1 | Determine Acquisition Type | x
2 | SAM | 1 | 1.2 | Select Suppliers | x
2 | SAM | 1 | 1.3 | Establish Supplier Agreements | x
2 | SAM | 2 |  | Satisfy Supplier Agreements
2 | SAM | 2 | 2.1 | Review COTS Products | x
2 | SAM | 2 | 2.2 | Execute the Supplier Agreement | x
2 | SAM | 2 | 2.3 | Accept the Acquired Product | x
2 | SAM | 2 | 2.4 | Transition Products | x
3 | RD | 1 |  | Develop Customer Requirements
3 | RD | 1 | 1.1-1 | Collect Stakeholder Needs |  | Capture Product Vision | Develop Lifestyle Snapshot | Lifestyle Snapshot | Stakeholder Issue Status (Report)
[6 empty] | Test a Customer Requirement (Scenario or QoS) | Conduct Exploratory Testing (for missing requirements) | ??? | Scenario Status Quality of Service Requirement Status (Reports)
3 | RD | 1 | 1.1-2 | Elicit Needs |  | Create Scenario | Brainstorm Scenarios | Scenario
[6 empty] | Capture Product Vision | Develop Lifestyle Snapshot | Lifestyle Snapshot
[6 empty] | Create QoS Requirement | Brainstorm QoS Requirements | Quality of Service Requirements
[6 empty] | Test a Customer Requirement (Scenario or QoS) | Conduct Exploratory Testing (for missing requirements) | ??? | Scenario Status Quality of Service Requirement Status (Reports)
3 | RD | 1 | 1.2 | Develop Customer Requirements |  | Create Scenario | Write Scenario, Storyboard Scenario, Write Qos Requirement, Write Security Requirements, Refine Personas | Scenario Quality of Service Requirements Threat Asset List | Storyboard Personas
3 | RD | 2 |  | Develop Product Requirements
3 | RD | 2 | 2.1 | Establish Product & Product Component Requirements |  | Create Product Requirements | Define Security Requirements | Security Requirements
[6 empty] | Create Product Requirements | Define Safety Requirements | Safety Requirements
[6 empty] | Create Product Requirements | Define Functional Requirements | Functional Requirements
3 | RD | 2 | 2.2 | Allocate Product Component Requirements |  | Create Product Requirements | Allocate Product Component Requirements | ??? | Product Component Requirements
3 | RD | 2 | 2.3 | Identify Interface Requirements |  | Create Product Requirements | Define Interface Requirements | Interface Requirements
3 | RD | 3 |  | Analyze and Validate Requirements
3 | RD | 3 | 3.1 | Establish Operational Concepts and Scenarios |  | Capture Product Vision | Develop Lifestyle Snapshot | Lifestyle Snapshot
[6 empty] | Create Scenarios | Write Scenario | Scenario
[6 empty] | Create QoS Requirements | Write QoS Requirement | Quality of Service Requirements
[6 empty] | Create Scenarios | Storyboard Scenarios | Storyboard | Scenario
[6 empty] | Create Product Requirements | Define Operational Requirements | Operational Requirements
3 | RD | 3 | 3.2 | Establish a Definition of Required Functionality |  | Create Product Requirements | Develop a Domain Model | Domain Model
[6 empty] | Create Product Requirements | Define Functional Requirements | Functional Requirements
3 | RD | 3 | 3.3 | Analyze Requirements |  | Create Product Requirements | Develop a Domain Model | Domain Model
[6 empty] | Create Product Requirements | Develop a UI Flow Model | UI Flow Model
3 | RD | 3 | 3.4-3 | Analyze Requirements to Achieve Balance |  | Create Scenario | Prioritize Scenarios | ??? | Scenario
[6 empty] | Create QoS Requirements | Prioritize QoS Requirements | ??? | Quality of Service Requirements
[6 empty] | Create Product Requirements | Develop a Domain Model | Domain Model
[6 empty] | Create Product Requirements | Develop a UI Flow Model | UI Flow Model
[6 empty] | Create Product Requirements | Prioritize Functionality | ??? | Functional Requirements
3 | RD | 3 | 3.5-1 | Validate Requirements |  | Create Scenarios | Scenarios Review | Review Report
[6 empty] | Create QoS Requirements | QoS Requirements Review | Review Report
3 | RD | 3 | 3.5-2 | Validate Requirements with Comprehensive Methods |  | Create Product Requirements | Requirements Review | Review Report | Requirements Review Minutes
3 | TS | 1 |  | Select Product Component Solutions
3 | TS | 1 | 1.1-1 | Develop Alternative Solutions and Selection Criteria |  | Create (Solution) Architecture | Create a Proof of Concept | Proof of Concept Architectural Solutions | Plan or Design for Proof of Concept (work product)
3 | TS | 1 | 1.1-2 | Developer Detailed Alternative Solutions and Selection Criteria |  | Create (Solution) Architecture | Create a Proof of Concept | Proof of Concept | Plan or Design for Proof of Concept (work product)
[6 empty] | Create (Solution) Architecture | Create .Net Application Partitioning Designs | Application Connection Diagram
3 | TS | 1 | 1.2-2 | Evolve Operational Concepts and Scenarios |  | Create (Solution) Architecture | Analyze Scenarios against Architectural Concept | Architectural Scenario Validation Document
[6 empty] | Create Product Requirements | Develop a Domain Model | Domain Model
[6 empty] | Create Product Requirements | Define Operational Requirements | Operational Requirements
3 | TS | 1 | 1.3 | Select Product Component Solutions |  | Create (Solution) Architecture | Select Solutions | Solution Architecture
3 | TS | 2 |  | Develop the Design
3 | TS | 2 | 2.1 | Design the Product or Product Component |  | Create (Solution) Architecture | Create .Net Application Partitioning Designs | Application Connection Diagram
[6 empty] | Create (Solution) Architecture | Develop Threat Model | Threat Model
[6 empty] | Create (Solution) Architecture | Develop Performance Model | Performance Model
3 | TS | 2 | 2.2-3 | Establish a Technical Data Package |  | Create (Solution) Architecture | Create Infrastructure Architecture & Documentation Guidelines | Technical Data Package
[6 empty] | Implement a Dev Task | Design | Technical Data Package
3 | TS | 2 | 2.3-1 | Establish Interface Descriptions |  | Create (Solution) Architecture | Design System Architecture and Deployment | Solution Architecture Interface Requirements
3 | TS | 2 | 2.3-3 | Design Interfaces Using Criteria |  | Create (Solution) Architecture | Design System Architecture and Deployment | Solution Architecture Interface Requirements
3 | TS | 2 | 2.4-3 | Perform Make, Buy, Reuse Analysis |  | Create (Solution) Architecture | Select Solutions | Solution Architecture
3 | TS | 3 |  | Implement the Product Design
3 | TS | 3 | 3.1 | Implement the Design |  | Implement a Dev Task | Write Code | Source Code
[6 empty] | Implement a Dev Task | Refactor Code | Source Code | Review Comments
[6 empty] | Fix a Bug | Code Fix for Bug | Source Code | Bugs
[6 empty] | Fix a Bug | Refactor Code | Source Code | Bugs
3 | TS | 3 | 3.2 | Develop Product Support Documentation |  | Develop Documentation |  | Product Documentation | Documentation Plan
3 | PI | 1 |  | Prepare for Product Integration
3 | PI | 1 | 1.1-1 | Determine Integration Sequence |  | Establish Environments | Plan Product Integration | Product Integration Plan
3 | PI | 1 | 1.2-2 | Establish the Product Integration Environment |  | Establish Environments | Establish Product Integration Environment | Integration Environment | Product Integration Plan
[6 empty] | Establish Environments | Verify Product Integration Environments | Integration Environment | Review Comments Peer Review Data
3 | PI | 1 | 1.3-3 | Establish Product Integration Procedures and Criteria |  | Establish Environments | Establish Product Integration Environment | Product Integration Plan | Rationale for Integration Sequence Support Documentation for Integration Environment
3 | PI | 2 |  | Ensure Interface Compatibility
3 | PI | 2 | 2.1 | Review Interface Descriptions for Completeness |  | Create (Solution) Architecture | Review System Architecture and Deployment Diagram | Solution Architecture Application System Diagram | Review Comments Peer Review Data
3 | PI | 2 | 2.2 | Manage Interfaces |  | Create (Solution) Architecture | Manage Interface Definitions | Solution Architecture Interface Requirements
3 | PI | 3 |  | Assemble Product Components and Deliver the Product
3 | PI | 3 | 3.1 | Confirm Readiness of Product Components for Integration |  | Build a Product | Accept a Build | Build | Build Notes Build Report
[6 empty] | Implement a Dev Task | Review Code | Source Code | Review Comments Peer Review Data
[6 empty] | Implement a Dev Task | Integrate Code Changes | Source Code | Review Comments Peer Review Data
[6 empty] | Fix a Bug | Review Code | Source Code | Review Comments Peer Review Data
[6 empty] | Fix a Bug | Integrate Code Changes | Source Code | Review Comments Peer Review Data
3 | PI | 3 | 3.2 | Assemble Product Components |  | Build a Product | Start Build | Build | Build Notes Build Report
3 | PI | 3 | 3.3 | Evaluate Assembled Product Components |  | Build a Product | Run Tests and Verify Build | Build Report | Build
[6 empty] | Release a Product | Accept Product for Release | Release Evaluation Results | Release Notes Release Acceptance Criteria Build
3 | PI | 3 | 3.4 | Package and Deliver the Product or Product Component |  | Release a Product | Create Release Notes | Release Notes
[6 empty] | Release a Product | Package Product | Release Candidate Build
3 | VER | 1 |  | Prepare for Verification
3 | VER | 1 | 1.1 | Select Work Products for Verification |  | Plan an Iteration, Implement a Dev Task, Fix a Bug | Schedule Scenario for Development & Test, Create or Update a Unit Test | Unit Test
3 | VER | 1 | 1.2-2 | Establish the Verification Environment |  | Establish Environments | Establish a Unit Test Environment | Unit Test Environment
3 | VER | 1 | 1.3-3 | Establish Verification Procedures |  | Verify a Product Requirement | Develop Tests | Test Cases (work product)
[6 empty] | Implement a Dev Task | Create or Update a System Verification Test | System Test (work product)
[6 empty] | Implement a Dev Task | Write or Update a Unit Test | Unit Test
[6 empty] | Establish Environments | Select Project Verification Guidelines | Test Approach (work product)
3 | VER | 2 |  | Perform Peer Reviews
3 | VER | 2 | 2.1 | Prepare for Peer Reviews |  | Implement a Dev Task | Perform Code Analysis | Source Code Code Analysis Guidelines Project Coding Guidelines Organization Coding Guidelines | Peer Review Data
[6 empty] | Create (Solution) Architecture | Select Solutions | Solution Architecture
[6 empty] | Implement a Dev Task | Prepare for Design Review | Application System Diagram
[6 empty] | Implement a Dev Task | Prepare for Code Review | Source Code Code Analysis Guidelines Project Coding Guidelines Organization Coding Guidelines
[6 empty] | Fix a Bug | Prepare for Code Review | Source Code Code Analysis Guidelines Project Coding Guidelines Organization Coding Guidelines
3 | VER | 2 | 2.2 | Conduct Peer Reviews |  | Implement a Dev Task | Review Code | Peer Review Minutes Analysis Review Comments | Source Code Code Analysis Guidelines Project Coding Guidelines Organization Coding Guidelines
[6 empty] | Implement a Dev Task | Review Design | Peer Review Minutes Analysis Review Comments | Application System Diagram
[6 empty] | Fix a Bug | Review Code | Peer Review Minutes Analysis Review Comments | Source Code Code Analysis Guidelines Project Coding Guidelines Organization Coding Guidelines
[6 empty] | Fix a Bug | Review Fix Strategy | Peer Review Minutes Analysis Review Comments | ???
[6 empty] | Baseline Configuration Management | Review Configuration Management Guidelines | Peer Review Minutes Analysis Review Comments | Configuration Management Guidelines
[6 empty] | Manage Change Request | Review Change Requests | Peer Review Minutes Analysis Review Comments | Change Request
[6 empty] | Capture Product Vision | Review Vision Statement | Peer Review Minutes Analysis Review Comments | Vision Statement
[6 empty] | Create (Solution) Architecture | Review System Architecture and Deployment | Peer Review Minutes Analysis Review Comments | Solution Architecture Application System Diagram
[6 empty] | Issue Management | Corrective Action Review | Peer Review Minutes Analysis Review Comments | Corrective Actions
[6 empty] | Plan Project | Project Plan Review | Peer Review Minutes Analysis Review Comments | Project Plan
[6 empty] | Release a Product | Select Release Candidate | Peer Review Minutes Analysis Review Comments | Release Candidate Build
3 | VER | 2 | 2.3-2 | Analyze Peer Review Data |  | Iteration Closeout | Analyze Peer Review Data | Peer Review Minutes Analysis
[6 empty] | Establish Project Process | Evaluate Process | Project Process Definition
[6 empty] | Plan an Iteration | Plan Knowledge and Skills | Knowledge and Skills Plan
[6 empty] | Establish Environments | Select Static Analysis Rules and Guidelines | Static Analysis Rules Static Analysis Guidelines
[6 empty] | Establish Environments | Select Project Coding Guidelines | Organization Coding Guidelines Project Coding Guidelines
3 | VER | 3 |  | Verify Selected Work Products
3 | VER | 3 | 3.1 | Perform Verification |  | Implement a Dev Task | Perform Unit Test | Unit Test (Report)? | Unit Test
[6 empty] | Fix a Bug | Perform Unit Test | Unit Test (Report)? | Unit Test
[6 empty] | Close a Bug | Verify Fix | Bug
[6 empty] | Verify Product Requirement | Select and Run Tests | System Test
[6 empty] | Fix a Bug | Reproduce the Bug | Bug
3 | VER | 3 | 3.2-2 | Analyze Verification Results and Identify Corrective Actions |  | Stabilize Track | Triage Bugs | Corrective Action Log (Report) Corrective Action Plan (Task WI) | Change Request
[6 empty] | Verify Product Requirement | Open a Bug | System Test | Change Request
[6 empty] | Fix a Bug | Locate Cause of Bug | ??? | Change Request
[6 empty] | Fix a Bug | Decide Strategy for Fix | ??? | Change Request
3 | VAL | 1 |  | Prepare for Validation
3 | VAL | 1 | 1.1 | Select Products for Validation |  | Release a Product | Select Release Candidate | Release Candidate Build | Release Acceptance Criteria
3 | VAL | 1 | 1.2 | Establish the Validation Environment |  | Release a Product | Establish Product/Field/User Acceptance Test Environment | User Acceptance Test Environment Ready Signal
3 | VAL | 1 | 1.3 | Establish Validation Procedures and Criteria |  | Create Customer Requirement (Scenario or QoS) | Write User Acceptance Test Case | User Acceptance Test Criteria User Acceptance Test Procedures
[6 empty] | Test Customer Requirements | Develop Tests | User Acceptance Test
3 | VAL | 2 |  | Validate Product or Product Components
3 | VAL | 2 | 2.1 | Perform Validation |  | Test a Customer Requirement | Select and Run Tests | User Acceptance Test Results | User Acceptance Test
[6 empty] | Release a Product | User Acceptance Test | User Acceptance Test Results | User Acceptance Test
3 | VAL | 2 | 2.2 | Analyze Validation Results |  | Release a Product | Analyze UAT Results | Peer Review Data Review Comments | User Acceptance Test Results
[6 empty] | Stabilize Track | Triage Bugs | ??? | Bug
[6 empty] | Test a Customer Requirement | Open Bug | Bug
3 | OPF | 1 |  | Determine Process Improvement Opportunities
3 | OPF | 1 | 1.1 | Establish Organizational Process Needs | x
3 | OPF | 1 | 1.2 | Appraise the Organization's Processes | x
3 | OPF | 1 | 1.3 | Identify the Organization's Process Improvements | x
3 | OPF | 2 |  | Plan and Implement Process Improvement Activities
3 | OPF | 2 | 2.1 | Establish Process Action Plans | x
3 | OPF | 2 | 2.2 | Implement Process Action Plans | x
3 | OPF | 2 | 2.3 | Deploy Organizational Process Assets | x
3 | OPF | 2 | 2.4 | Incorporate Process Related Experiences into the Organizational Process Assets | x
3 | OPD | 1 |  | Establish Organizational Process Assets
3 | OPD | 1 | 1.1 | Establish Standard Processes |  | Establish Project Process | Evoke Organizational Process | Organizational Process Definition | VSTS process guidance, reports, queries
3 | OPD | 1 | 1.2 | Establish Lifecycle Model |  | Establish Project Process | Evoke Organizational Process | Organizational Process Definition | VSTS process guidance, reports, queries
3 | OPD | 1 | 1.3 | Establish Tailoring Criteria and Guidelines |  | Establish Project Process | Apply Tailoring Criteria and Guidelines | Tailoring Criteria and Guidelines
3 | OPD | 1 | 1.4 | Establish the Organization's Measurement Repository |  | Establish Project Process | Populate Organization Measurement Repository | VSTS database | VSTS process guidance, reports, queries
3 | OPD | 1 | 1.5 | Establish the Organization's Process Asset Library |  | Establish Project Process | Populate Organization Process Asset Library | VSTS process template, source control server
[6 empty] | Establish Project Process | Maintain Process Asset Library Catalog | VSTS source control server
3 | OT | 1 |  | Establish an Organizational Training Capability
3 | OT | 1 | 1.1 | Establish the Strategic Training Needs | x
3 | OT | 1 | 1.2 | Determine which Training Needs are the Responsibility of the Organization | x
3 | OT | 1 | 1.3 | Establish an Organizational Training Tactical Plan | x
3 | OT | 1 | 1.4 | Establish Training Capability | x
3 | OT | 2 |  | Provide Necessary Training
3 | OT | 2 | 2.1 | Deliver Training | x
3 | OT | 2 | 2.2 | Establish Training Records | x
3 | OT | 2 | 2.3 | Assess Training Effectiveness | x
3 | IPM | 1 |  | Use the Project's Defined Process
3 | IPM | 1 | 1.1 | Establish the Project's Defined Process |  | Establish Project Process |  | Project Process Definition Measurement Plan Project Data Management Plan | Measurement Server Organization Process Asset Library
[6 empty] | Plan Project | Define Project Lifecycle | Project Process Definition
3 | IPM | 1 | 1.2 | Use Organizational Process Assets for Planning Project Activities |  | Plan Project | Establish Budget and Schedule | Budget Schedule
[6 empty] | Plan Project | Plan Project Resources | Project Team and Organization Chart | Project Plan
[6 empty] | Plan Project | Plan Knowledge and Skills | Knowledge and Skills Plan
[6 empty] | Plan Project | Plan Stakeholder Involvement | Stakeholder Involvement Plan
3 | IPM | 1 | 1.3 | Integrate Plans |  | Plan Project | IPMO Plan Review | Peer Review Minutes Analysis Review Comments
3 | IPM | 1 | 1.4 | Manage the Project Using the Integrated Plans |  | Operational Management Track | Operations Review | Peer Review Minutes Analysis Review Comments
[6 empty] | Operational Management Track | IPMO Review | Peer Review Minutes Analysis Review Comments
3 | IPM | 1 | 1.5 | Contribute to the Organizational Process Assets |  | Iteration Closeout | Iteration Retrospective
[6 empty] | Project Closeout | Project Retrospective
[6 empty] | Establish Project Process | Populate Organization Process Asset Library | Work products/items
[6 empty] | Establish Project Process | Evoke Organizational Process | Improvement Suggestion | Organizational Process Definition
3 | IPM | 2 |  | Coordinate and Collaborate with Relevant Stakeholders
3 | IPM | 2 | 2.1 | Manage Stakeholder Involvement |  | Operational Management Track | Manage Stakeholder Involvement | Stakeholder Involvement Report | Stakeholder Involvement Plan
[6 empty] | Plan Iteration | Identify Stakeholders | Stakeholder List | Iteration Plan
[6 empty] | Plan Project | Identify Stakeholders | Stakeholder List | Project Plan
3 | IPM | 2 | 2.2 | Manage Dependencies |  | Operational Management Track | Manage Stakeholder Involvement | Stakeholder Involvement Report | Stakeholder Involvement Plan
[6 empty] | Operational Management Track | IPMO Meeting | Issue Log | Meeting minutes
3 | IPM | 2 | 2.3 | Resolve Coordination Issues |  | Operational Management Track | IPMO Meeting | Issue Log Issue Analysis | Issue Resolved Signal
3 | IPM | 3 |  | Use the Project's Shared Vision for IPPD
3 | IPM | 3 | 3.1 | Define Project's Shared Vision Context | x |  |  | Vision Statement
3 | IPM | 3 | 3.2 | Establish the Project's Shared Vision |  | Capture Product Vision | Write Vision Statement | Vision Statement
[6 empty] | Capture Product Vision | Define Personas | Personas
3 | IPM | 4 |  | Organize Integrated Teams for IPPD
3 | IPM | 4 | 4.1 | Determine Integrated Team Structure for the Project |  | Plan Iteration | Form Iteration Team | Org Chart (work product) | Iteration and Project Review Meeting Minutes (work product)
[6 empty] | Plan Project | Form Project Team
[6 empty] | Plan Project | Define Roles and Responsibilities
3 | IPM | 4 | 4.2 | Develop a Preliminary Distribution of Requirements to Integrated Teams | x
3 | IPM | 4 | 4.3 | Establish Integrated Teams |  | Plan Iteration | Form Iteration Team | Iteration Plan (work product) | Iteration Plan Review Minutes
[6 empty] | Plan Project | Form Project Team | Project Plan (work product) | Project Plan Review
[6 empty] | Plan Project | Establish Communication Plan
3 | RSKM | 1 |  | Prepare for Risk Management
3 | RSKM | 1 | 1.1 | Determine Risk Sources and Categories |  | Plan Project | Determine Risk Sources and Categories | Risk sources and categories (work product) | Risk taxonomy (process guidance), Risk management database (Risk WI's)
3 | RSKM | 1 | 1.2 | Define Risk Parameters |  | Plan Project | Define Risk Parameters | Process Guidance | Risk management database (Risk WI's)
3 | RSKM | 1 | 1.3 | Establish a Risk Management Strategy |  | Plan Project | Establish Risk Management Strategy | Process Guidance, Process template and enactment | Process Guidance, Risk monitoring activity (Task WI's)
3 | RSKM | 2 |  | Identify and Analyze Risks
3 | RSKM | 2 | 2.1 | Identify Risks |  | Risk Management | Identify Risks | Risk WI's | Risk Analysis activities (Task WI's)
3 | RSKM | 2 | 2.2 | Evaluate, Categorize, and Prioritize Risks |  | Risk Management | Analyze Risks | Risk WI's with priority and history
|  |  |  | ("") |  | Risk Management | Prioritize Risks
3 | RSKM | 3 |  | Mitigate Risks
3 | RSKM | 3 | 3.1 | Develop Risk Mitigation Plans |  | Risk Management | Select Risks for Mitigation | Risk WI - mitigation plan field | Risk WI - history
[6 empty] | Risk Management | Plan Risk Mitigation
3 | RSKM | 3 | 3.2 | Implement Risk Mitigation Plans |  | Risk Management | Implement Risk Mitigation Plans | Task WI's - linked to Risk WI's | Task and Risk WI - history
3 | IT | 1 |  | Establish Team Composition
3 | IT | 1 | 1.1 | Identify Team Tasks |  | Plan an Iteration | Form Iteration Team | Task WI's (by team member) | WI status (by team) Report
3 | IT | 1 | 1.2 | Identify Needed Knowledge and Skills |  | Plan an Iteration | Identify Knowledge and Skills | Knowledge and skills Plan (work product) | Training Records (work product)
[6 empty] | Plan Project | Identify Knowledge and Skills | Knowledge and skills Plan (work product) | Training Records (work product)
3 | IT | 1 | 1.2 | Assign Appropriate Team Members |  | Plan an Iteration | Form Iteration Team | Team assignments - person against role - Project Team Org Chart (work product) | Task WI's with history and time recording
[6 empty] | Plan Project | Form Project Team | Team assignments - person against role - Project Team Org Chart (work product) | Task WI's with history and time recording
3 | IT | 2 |  | Govern Team Operation
3 | IT | 2 | 2.1 | Establish a Shared Vision |  | Capture Product Vision | Write Vision Statement | Vision Statement (work product) | Project Launch Review WI and Meeting Minutes
|  |  |  | ("") |  | Capture Product Vision | Define Personas | Personas (work product)
3 | IT | 2 | 2.2 | Establish a Team Charter |  | Plan Project | Establish Team Charter | Team Charter (work product)
3 | IT | 2 | 2.3 | Define Roles and Responsibilities |  | Plan Project | Define Roles & Responsibilities | Team Charter (work product)
[6 empty] | Plan Iteration | Define Roles & Responsibilities | Iteration Update of Team Charter (work product)
3 | IT | 2 | 2.4 | Establish Operating Procedures |  | Plan Project | Establish Operating Procedures | Communication Plan and tailored Project / Iteration Process Template
3 | IT | 2 | 2.5 | Collaborate among Interfacing Teams |  | Plan Project | Establish Communication Plan |  | Communication Plan
[6 empty] | Plan Iteration | Establish Communication Plan |  | Communication Plan
[6 empty] | Plan Project | Form Project Team
[6 empty] | Operational Management Track | IPMO Meeting | IPMO Meeting Minutes | Triage activity recorded in WI history
3 | ISM | 1 |  | Analyze and Select Sources of Products
3 | ISM | 1 | 1.1 | Analyze Potential Sources of Products | x
3 | ISM | 1 | 1.2 | Evaluate and Determine Sources of Products | x
3 | ISM | 2 |  | Coordinate with Suppliers
3 | ISM | 2 | 2.1 | Monitor Selected Supplier Processes | x
3 | ISM | 2 | 2.2 | Evaluate Selected Supplier Work Products | x
3 | ISM | 2 | 2.3 | Revise the Supplier Agreement or Relationship | x
3 | DAR | 1 |  | Evaluate Alternatives
3 | DAR | 1 | 1.1 | Establish Guidelines for Decision Analysis |  | Create (Solution) Architecture | Assess Alternatives (LAAAM) | ??? | ???
3 | DAR | 1 | 1.2 | Establish Evaluation Criteria |  | Create (Solution) Architecture | Assess Alternatives (LAAAM) | LAAAM papers, Process Guidance | LAAAM papers, Process Guidance
3 | DAR | 1 | 1.3 | Identify Alternative Solutions |  | Create (Solution) Architecture | Create Alternative .Net Application Partitioning Designs | Technology Strategies | LAAAM Assessment Matrix
3 | DAR | 1 | 1.4 | Select Evaluation Methods |  | Create (Solution) Architecture | Assess Alternatives (LAAAM) | ??? | LAAAM Assessment Matrix
3 | DAR | 1 | 1.5 | Evaluate Alternatives |  | Create (Solution) Architecture | Assess Alternatives (LAAAM) | LAAAM Assessment Matrix | Select Architecture (Review) Meeting Minutes
3 | DAR | 1 | 1.6 | Select Solutions |  | Create (Solution) Architecture | Select Solutions | LAAAM Assessment Matrix | Select Architecture (Review) Meeting Minutes
3 | OEI | 1 |  | Provide IPPD Infrastructure
3 | OEI | 1 | 1.1 | Establish the Organization's Shared Vision | x
3 | OEI | 1 | 1.2 | Establish an Integrated Work Environment | x
3 | OEI | 1 | 1.3 | Identify IPPD-Unique Skill Requirements | x
3 | OEI | 2 |  | Manage People for Integration
3 | OEI | 2 | 2.1 | Establish Leadership Mechanisms | x
3 | OEI | 2 | 2.2 | Establish Incentives for Integration | x
3 | OEI | 2 | 2.3 | Establish Mechanisms to Balance Team and Home Organization Responsibilities | x
4 | OPP | 1 |  | Establish Performance Baselines and models
4 | OPP | 1 | 1.1 | Select Processes |  | Operational Management Track | Operations Review
4 | OPP | 1 | 1.2 | Establish Process Performance Measures |  | Operational Management Track | Operations Review
4 | OPP | 1 | 1.3 | Establish Quality and Process Performance Objectives | x
4 | OPP | 1 | 1.4 | Establish Process Performance Baselines | x
4 | OPP | 1 | 1.5 | Establish Process Performance Models | x
4 | QPM | 1 |  | Quantitatively Manage the Project
4 | QPM | 1 | 1.1 | Establish the Project's Objectives | x
4 | QPM | 1 | 1.2 | Compose the Defined Process | x
4 | QPM | 1 | 1.3 | Select the Subprocesses that Will Be Statistically Managed | x
4 | QPM | 1 | 1.4 | Manage Project Performance |  | Operational Management Track | Operations Review
4 | QPM | 2 |  | Statistically Manage Subprocesses Performance
4 | QPM | 2 | 2.1 | Select Measures and Analytic Techniques |  | Operational Management Track | Operations Review
4 | QPM | 2 | 2.2 | Apply Statistical Methods to Understand Variation |  | Operational Management Track | Operations Review
4 | QPM | 2 | 2.3 | Monitor Performance of the Selected Subprocesses |  | Operational Management Track | Operations Review
4 | QPM | 2 | 2.4 | Record Statistical Management Data | x
5 | OID | 1 |  | Select Improvements
5 | OID | 1 | 1.1 | Collect and Analyze Improvement Proposals |  | Operational Management Track | Operations Review
5 | OID | 1 | 1.2 | Identify and Analyze Innovations |  | Operational Management Track | Operations Review
5 | OID | 1 | 1.3 | Pilot Improvements | x
5 | OID | 1 | 1.4 | Select Improvements for Deployment | x
5 | OID | 2 |  | Deploy Improvements
5 | OID | 2 | 2.1 | Plan the Deployment | x
5 | OID | 2 | 2.2 | Manage the Deployment | x
5 | OID | 2 | 2.3 | Measure Improvement Effects | x
5 | CAR | 1 |  | Determine Causes of Defects | x
5 | CAR | 1 | 1.1 | Select Defect Data for Analysis |  | Operational Management Track | Operations Review
5 | CAR | 1 | 1.2 | Analyze Causes | x
5 | CAR | 2 |  | Address Causes of Defects | x
5 | CAR | 2 | 2.1 | Implement the Action Proposals | x
5 | CAR | 2 | 2.2 | Evaluate the Effect of Changes | x
5 | CAR | 2 | 2.3 | Record Data | x
Total |  |  | 189 |  | 56 | 133